KEMENTERIAN KOMUNIKASI DAN DIGITAL

Direktorat Jenderal Penyelenggaraan Pos dan Informatika

MONTHLY PROGRESS
REPORT

TELKOM INSIGHT HUB

Laporan Kemajuan Bulanan — April 2026

| Nomor Dokumen: | TIH-MPR-2026-04 |
| --- | --- |
| Versi: | 1.0 |
| Tanggal: | April 2026 |
| Klasifikasi: | Internal — Terbatas |
| Status: | Draft untuk Persetujuan |

# 1. Executive Summary

Laporan ini merangkum kemajuan pengembangan sistem Telkom Insight Hub untuk periode April 2026. Secara keseluruhan, pengembangan berjalan sesuai dengan jadwal yang direncanakan. Modul inti (Manajemen Data Telekomunikasi, Registrasi & Verifikasi) telah selesai 100%. Modul integrasi (BPS, KOMINFO) mencapai 85%, dan modul analitik (Potensi Pasar, Visualisasi) mencapai 70%. Fokus bulan ini adalah penyelesaian integrasi BPS dan optimasi scoring algorithm.

# 2. Overall Progress

| Modul | Target | Aktual | Status | Catatan |
| --- | --- | --- | --- | --- |
| Authentication & RBAC | 100% | 100% | ✓ Selesai | JWT + 6 roles implemented |
| Manajemen Data Telekomunikasi | 100% | 100% | ✓ Selesai | 8 jenis layanan, CRUD + Excel |
| Registrasi & Verifikasi | 100% | 100% | ✓ Selesai | Full workflow + admin dashboard |
| Integrasi BPS | 90% | 85% | ○ On Track | Catalog search & viz remaining |
| Sinkronisasi KOMINFO Tarif | 90% | 85% | ○ On Track | Periodic sync tested |
| Potensi Pasar Telekomunikasi | 80% | 70% | ○ On Track | V2 scoring in progress |
| Dashboard & Visualisasi | 80% | 75% | ○ On Track | Main dashboard complete |
| Support & Ticketing | 100% | 100% | ✓ Selesai | WebSocket real-time |
| FAQ Management | 100% | 100% | ✓ Selesai | CRUD + categories |
| User Management | 100% | 100% | ✓ Selesai | Admin panel complete |
| Permission Management | 95% | 90% | ○ On Track | Field-level in progress |
| Integrasi e-Telekomunikasi | 90% | 85% | ○ On Track | Service key auth active |
| DevSecOps & Security | 90% | 90% | ✓ Selesai | Helmet, rate limit, audit |
| Documentation | 80% | 75% | ○ On Track | 20+ docs, API ref complete |

# 3. Milestone Achievement

| Milestone | Target Date | Actual | Status |
| --- | --- | --- | --- |
| Core Architecture Setup | Jan 2026 | Jan 2026 | ✓ Completed |
| Authentication & RBAC | Jan 2026 | Jan 2026 | ✓ Completed |
| Telekom Data CRUD | Feb 2026 | Feb 2026 | ✓ Completed |
| Company Registration | Feb 2026 | Feb 2026 | ✓ Completed |
| BPS Integration Phase 1 | Mar 2026 | Mar 2026 | ✓ Completed |
| KOMINFO Tariff Sync | Mar 2026 | Mar 2026 | ✓ Completed |
| Telecom Potential V1 | Mar 2026 | Apr 2026 | ○ Delayed 2 weeks |
| Dashboard & Visualization | Apr 2026 | Apr 2026 | ○ In Progress |
| BPS Integration Phase 2 | Apr 2026 | Apr 2026 | ○ In Progress |
| Telecom Potential V2 | Apr 2026 | May 2026 | ○ Planned |
| UAT Preparation | May 2026 | - | ○ Planned |
| Production Deployment | Jun 2026 | - | ○ Planned |

# 4. Key Achievements This Month

1. BPS Configuration Module — Implementasi lengkap modul konfigurasi BPS dengan API key management, area monitoring, dan variable registration

2. Telecom Potential Dashboard — Implementasi dashboard potensi pasar dengan interactive Mapbox map, radar chart, dan sortable table

3. Backend Integration Services — Implementasi BPS API Fetcher Service (23KB), Data Normalizer Service (17KB), dan Telecom Potential V2 Service (19KB)

4. Data Migration — Migrasi data lokasi (provinsi & kabupaten) dan data perizinan dari sistem legacy

5. Security Enhancement — Implementasi DevSecOps monitoring dashboard dengan audit logging dan security metrics

# 5. Technical Metrics

| Metrik | Bulan Lalu | Bulan Ini | Trend |
| --- | --- | --- | --- |
| Total Pages/Views | 18 | 22 | ↑ +4 |
| Total Components | 48 | 55+ | ↑ +7 |
| Total API Endpoints | 52 | 60+ | ↑ +8 |
| Total Database Tables | 35 | 40+ | ↑ +5 |
| Backend Services | 6 | 12 | ↑ +6 |
| Test Coverage | 45% | 55% | ↑ +10% |
| Documentation Files | 15 | 20+ | ↑ +5 |
| Code Quality (ESLint) | 92% | 95% | ↑ +3% |

# 6. Issues & Risks

| ID | Issue/Risk | Severity | Status | Mitigation |
| --- | --- | --- | --- | --- |
| ISS-01 | BPS API rate limit causing slow sync | Medium | Mitigated | Implemented queuing & retry |
| ISS-02 | Telecom Potential V2 complexity | Low | In Progress | Phased implementation |
| ISS-03 | Large dataset pagination performance | Medium | Resolved | Server-side pagination + indexing |
| RSK-01 | External API downtime during sync | Medium | Monitored | Graceful degradation implemented |
| RSK-02 | Data inconsistency between sources | Low | Monitored | Validation checks in normalizer |

# 7. Plan for Next Month (May 2026)

| Task | Priority | Estimated Effort | Assignee |
| --- | --- | --- | --- |
| Complete Telecom Potential V2 scoring | High | 5 days | Backend Team |
| BPS data visualization enhancement | High | 3 days | Frontend Team |
| Field-level permission implementation | Medium | 3 days | Backend Team |
| UAT scenario preparation (528 scenarios) | High | 5 days | QA Team |
| Performance optimization & load testing | Medium | 3 days | DevOps Team |
| Documentation completion & review | Medium | 2 days | All Teams |
| Security audit & penetration testing | High | 3 days | Security Team |
| Mobile responsive optimization | Low | 2 days | Frontend Team |

# 8. Resource Allocation

| Area | Allocated | Utilized | Utilization % |
| --- | --- | --- | --- |
| Frontend Development | 2 developers | 2 developers | 100% |
| Backend Development | 2 developers | 2 developers | 100% |
| DevOps & Infrastructure | 1 engineer | 1 engineer | 80% |
| QA & Testing | 1 tester | 1 tester | 60% |
| Project Management | 1 PM | 1 PM | 100% |

# 9. Budget Status

| Kategori | Budget | Spent | Remaining | % Used |
| --- | --- | --- | --- | --- |
| Development | - | - | - | - |
| Infrastructure | - | - | - | - |
| Licensing | - | - | - | - |
| Testing | - | - | - | - |
| Total | - | - | - | - |

* Budget details to be filled by project management

# 10. Action Items

| # | Action Item | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| 1 | Finalize BPS integration Phase 2 | Backend Lead | 15 May 2026 | Open |
| 2 | Complete Telecom Potential V2 | Backend Lead | 20 May 2026 | Open |
| 3 | Prepare UAT scenarios document | QA Lead | 25 May 2026 | Open |
| 4 | Security audit report | DevOps | 30 May 2026 | Open |
| 5 | Stakeholder demo & feedback | PM | 30 May 2026 | Open |

# Lembar Persetujuan — Monthly Progress Report

| Peran | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Disusun oleh (Prepared by) |  |  |  |
| Diperiksa oleh (Reviewed by) |  |  |  |
| Disetujui oleh (Approved by - Teknis) |  |  |  |
| Disetujui oleh (Approved by - Manajemen) |  |  |  |

### Catatan Revisi:

| Versi | Tanggal | Penulis | Deskripsi Perubahan | Status |
| --- | --- | --- | --- | --- |
| 1.0 | April 2026 | Tim Pengembangan | Dokumen awal | Draft |