## SUMMARY
UAT SCENARIOS SUMMARY — TELKOM INSIGHT HUB
Kementerian Komunikasi dan Digital — Direktorat Jenderal PPI
# | Module Code | Module Name | Scenarios | Priority High | Sheet
1 | AUTH | Authentication & Login | 25 | 13 | AUTH
2 | REG | Public Registration | 28 | 13 | REG
3 | COMP | Company Verification | 32 | 11 | COMP
4 | TDATA | Telekom Data Management | 36 | 14 | TDATA
5 | SVC | Service Type Pages | 26 | 10 | SVC
6 | BPSC | BPS Configuration | 21 | 6 | BPSC
7 | BPSS | BPS Survey & Variable Management | 19 | 3 | BPSS
8 | BPSV | BPS Data Visualization | 24 | 7 | BPSV
9 | TPOT | Telecom Market Potential | 29 | 5 | TPOT
10 | DASH | Dashboard & Analytics | 20 | 3 | DASH
11 | TICK | Support & Ticketing | 28 | 10 | TICK
12 | FAQ | FAQ Management | 17 | 5 | FAQ
13 | USER | User Management | 20 | 8 | USER
14 | PERM | Permission Management | 18 | 10 | PERM
15 | INTG | Integrations Dashboard | 20 | 8 | INTG
16 | SEC | Security & DevSecOps | 24 | 16 | SEC
17 | RBAC | RBAC Enforcement | 16 | 14 | RBAC
18 | NAV | Navigation & Layout | 21 | 2 | NAV
19 | EXIM | Data Export & Import | 18 | 6 | EXIM
20 | LOC | Location Management | 13 | 5 | LOC
21 | RT | Real-time & WebSocket | 13 | 5 | RT
22 | PERF | Performance & Load | 16 | 3 | PERF
23 | ERR | Error Handling & Edge Cases | 22 | 5 | ERR
24 | DEPL | Deployment & Health Check | 22 | 10 | DEPL
| TOTAL |  | 528 | 192
DOCUMENT SIGN-OFF / PERSETUJUAN DOKUMEN
Peran | Nama | Jabatan | Tanda Tangan | Tanggal
Disusun oleh (Prepared by)
QA Lead (Test Lead)
Project Manager (PM)
Teknis Lead (Technical Approval)
Stakeholder (Business Approval)
Management (Final Sign-off)
Dokumen UAT ini berisi 528 skenario pengujian pada 24 modul. Seluruh skenario harus dieksekusi dan ditandatangani sebelum sistem dapat dinyatakan Production Ready.
Nomor Dokumen: TIH-UAT-2026-001 ¦ Versi: 1.0 ¦ Tanggal: April 2026 ¦ Total Scenarios: 528

## AUTH
UAT SCENARIOS — Authentication & Login
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Authentication & Login
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-AUTH-001 | Login with valid credentials | User registered in system | 1. Navigate to login page 2. Enter valid email 3. Enter valid password 4. Click Login | User logged in, redirected to dashboard, JWT token received | High
2 | UAT-AUTH-002 | Login with invalid password | User registered in system | 1. Navigate to login page 2. Enter valid email 3. Enter wrong password 4. Click Login | Error message displayed, login rejected | High
3 | UAT-AUTH-003 | Login with non-existent email | No account with test email | 1. Navigate to login page 2. Enter non-existent email 3. Enter any password 4. Click Login | Error message: account not found | High
4 | UAT-AUTH-004 | Login with empty fields | Login page open | 1. Leave email empty 2. Leave password empty 3. Click Login | Validation error shown for required fields | High
5 | UAT-AUTH-005 | Login via e-Telekomunikasi | User has e-Telekomunikasi account | 1. Click 'Login via e-Telekomunikasi' 2. Enter e-Telekomunikasi credentials 3. Authenticate | User logged in via external auth, profile synced | High
6 | UAT-AUTH-006 | JWT token refresh | User logged in, token about to expire | 1. Wait for token expiration 2. Make API request 3. System auto-refreshes token | New access token issued, session continues | High
7 | UAT-AUTH-007 | Logout | User logged in | 1. Click Logout button 2. Confirm logout | Session cleared, cookies removed, redirected to login | High
8 | UAT-AUTH-008 | Rate limiting on login | Login page open | 1. Attempt login 100+ times in 15 min 2. Use wrong credentials each time | Rate limit triggered, 429 response returned | Medium
9 | UAT-AUTH-009 | Remember me / persistent session | Login page open | 1. Login with valid credentials 2. Close browser 3. Reopen and navigate to dashboard | Refresh token restores session within 30 days | Medium
10 | UAT-AUTH-010 | Password validation on login | Login page open | 1. Enter email with spaces 2. Enter password < 8 chars | Client-side validation errors shown | Low
11 | UAT-AUTH-011 | Session expiry handling | User logged in, session expired | 1. Wait for access token to expire 2. Attempt navigation 3. Refresh token also expired | User redirected to login page with session expired message | High
12 | UAT-AUTH-012 | Concurrent session handling | User logged in on device A | 1. Login on device B with same credentials 2. Verify both sessions active | Both sessions remain active (multi-device support) | Medium
13 | UAT-AUTH-013 | CSRF protection verification | Login page open | 1. Attempt cross-site login request 2. Verify CSRF token requirement | Cross-site request blocked | High
14 | UAT-AUTH-014 | Login audit trail | Admin has access to audit logs | 1. Login as user 2. Check audit_logs table 3. Verify login event recorded | Login event logged with timestamp, IP, user agent | Medium
15 | UAT-AUTH-015 | Email check availability | Registration page open | 1. Enter existing email 2. Wait for validation | Email marked as unavailable | Medium
16 | UAT-AUTH-016 | Email check for new email | Registration page open | 1. Enter new unique email 2. Wait for validation | Email marked as available | Medium
17 | UAT-AUTH-017 | Login with SQL injection attempt | Login page open | 1. Enter SQL injection in email field 2. Click Login | Input sanitized, login fails safely | High
18 | UAT-AUTH-018 | Login with XSS in email field | Login page open | 1. Enter <script> tag in email 2. Click Login | XSS attempt sanitized, no script execution | High
19 | UAT-AUTH-019 | Token tampering detection | User logged in | 1. Manually modify JWT payload 2. Make API request | Tampered token rejected, 401 returned | High
20 | UAT-AUTH-020 | Refresh token reuse prevention | Refresh token used | 1. Use refresh token 2. Try to reuse same token | Reused token rejected (rotation enforced) | High
21 | UAT-AUTH-021 | Login page accessibility | Login page open | 1. Navigate with keyboard only 2. Use screen reader | All form elements accessible via keyboard | Low
22 | UAT-AUTH-022 | Password masking on input | Login page open | 1. Type password 2. Verify masked display | Password characters masked | Low
23 | UAT-AUTH-023 | Login redirect after session timeout | Session expired | 1. Session times out 2. User tries action 3. Redirect to login 4. Login 5. Redirect back | User returned to original page after login | Medium
24 | UAT-AUTH-024 | Login form autofill | Browser with saved credentials | 1. Open login page 2. Verify browser autofill works | Login credentials auto-filled from browser | Low
25 | UAT-AUTH-025 | Login error message clarity | Login failed | 1. Fail login 2. Read error message | Error message helpful without revealing user existence | Medium
Total Scenarios: |  | 25
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## REG
UAT SCENARIOS — Public Registration
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Public Registration
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-REG-001 | Register with complete data | Registration page open | 1. Fill all required fields 2. Upload all documents 3. Fill PIC data 4. Submit | Registration successful, status: submitted | High
2 | UAT-REG-002 | Register with missing required fields | Registration page open | 1. Leave company name empty 2. Submit | Validation error for required fields | High
3 | UAT-REG-003 | Upload NIB document | Registration form open | 1. Click upload NIB 2. Select PDF file 3. Verify upload | NIB document uploaded and previewed | High
4 | UAT-REG-004 | Upload NPWP document | Registration form open | 1. Click upload NPWP 2. Select PDF file 3. Verify upload | NPWP document uploaded and previewed | High
5 | UAT-REG-005 | Upload Akta Pendirian | Registration form open | 1. Click upload Akta 2. Select PDF file | Akta document uploaded successfully | High
6 | UAT-REG-006 | Upload KTP PIC | Registration form open | 1. Click upload KTP 2. Select image file | KTP uploaded and previewed | High
7 | UAT-REG-007 | Upload invalid file type | Registration form open | 1. Try to upload .exe file | File type rejected with error message | High
8 | UAT-REG-008 | Upload oversized file (>10MB) | Registration form open | 1. Try to upload file > 10MB | File size limit error displayed | Medium
9 | UAT-REG-009 | Fill PIC information | Registration form open | 1. Enter PIC name 2. Enter PIC phone 3. Enter PIC email 4. Enter PIC position | PIC data saved successfully | High
10 | UAT-REG-010 | Register with existing email | Email already registered | 1. Enter existing email 2. Submit | Error: email already registered | High
11 | UAT-REG-011 | Register with valid NIB format | Registration form open | 1. Enter valid NIB number 2. Verify format | NIB accepted | Medium
12 | UAT-REG-012 | Register with invalid NIB | Registration form open | 1. Enter invalid NIB format 2. Verify | Validation error shown | Medium
13 | UAT-REG-013 | View registration confirmation | Registration submitted | 1. Complete registration 2. View confirmation page | Confirmation with status 'submitted' shown | High
14 | UAT-REG-014 | Multi-step form navigation | Registration form open | 1. Fill step 1 2. Go to step 2 3. Go back to step 1 4. Verify data preserved | Data persisted across form steps | Medium
15 | UAT-REG-015 | Form auto-save | Registration form partially filled | 1. Fill some fields 2. Navigate away 3. Return to form | Previously entered data still present | Low
16 | UAT-REG-016 | Location selector - Province | Registration form open | 1. Open province dropdown 2. Select 'DKI Jakarta' | Province selected, kabupaten list updates | High
17 | UAT-REG-017 | Location selector - Kabupaten | Province selected | 1. Open kabupaten dropdown 2. Select kabupaten | Kabupaten selected successfully | High
18 | UAT-REG-018 | Phone number validation | Registration form open | 1. Enter invalid phone format 2. Verify validation | Phone number validation error shown | Medium
19 | UAT-REG-019 | NPWP format validation | Registration form open | 1. Enter invalid NPWP 2. Verify validation | NPWP validation error shown | Medium
20 | UAT-REG-020 | Registration form responsive | Mobile device/viewport | 1. Open registration on mobile 2. Verify all fields accessible | Form renders correctly on mobile | Low
21 | UAT-REG-021 | Registration with special chars in name | Registration form open | 1. Enter company name with special characters 2. Submit | Special characters handled correctly | Medium
22 | UAT-REG-022 | Registration form step indicator | Registration form open | 1. View step indicator 2. Progress through steps | Step indicator shows current progress | Low
23 | UAT-REG-023 | Registration terms acceptance | Registration form last step | 1. Try submit without accepting terms 2. Accept terms 3. Submit | Terms must be accepted before submission | Medium
24 | UAT-REG-024 | Registration success redirect | Registration completed | 1. Complete registration 2. Verify redirect | Redirected to confirmation/login page | Medium
25 | UAT-REG-025 | Duplicate company registration | Company already registered | 1. Enter same company NIB 2. Submit | Duplicate company detection warning | High
26 | UAT-REG-026 | Registration field length limits | Registration form open | 1. Enter very long text in fields 2. Verify limits | Character limits enforced on all fields | Medium
27 | UAT-REG-027 | Registration captcha | Registration form | 1. Verify captcha/bot protection 2. Complete captcha | Bot protection active on registration | Medium
28 | UAT-REG-028 | Registration loading state | Form submitting | 1. Click submit 2. Observe loading state | Submit button disabled, loading indicator shown | Low
Total Scenarios: |  | 28
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## COMP
UAT SCENARIOS — Company Verification
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Company Verification
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-COMP-001 | View pending companies | Admin logged in | 1. Navigate to Company Management 2. Filter by status 'submitted' | List of pending companies displayed | High
2 | UAT-COMP-002 | Review company details | Admin on Company Management | 1. Click on a company 2. View all submitted data | Company details and documents displayed | High
3 | UAT-COMP-003 | Approve company | Company in 'in_review' status | 1. Review documents 2. Click 'Verify' 3. Confirm | Status changed to 'verified', user notified | High
4 | UAT-COMP-004 | Reject company | Company in 'in_review' status | 1. Review documents 2. Click 'Reject' 3. Enter reason 4. Confirm | Status changed to 'rejected' with reason | High
5 | UAT-COMP-005 | Request correction | Company in 'in_review' status | 1. Review documents 2. Click 'Needs Correction' 3. Add correction notes | Status changed to 'needs_correction', notes saved | High
6 | UAT-COMP-006 | View correction notes | Pelaku usaha logged in | 1. Check company status 2. View correction notes | Correction notes from admin displayed | High
7 | UAT-COMP-007 | Re-submit after correction | Company status 'needs_correction' | 1. Fix identified issues 2. Re-upload documents 3. Re-submit | Status changed back to 'submitted' | High
8 | UAT-COMP-008 | Filter companies by status | Admin on Company Management | 1. Select status filter 2. Apply filter | Companies filtered by selected status | Medium
9 | UAT-COMP-009 | Search company by name | Admin on Company Management | 1. Enter company name in search 2. Submit search | Matching companies displayed | Medium
10 | UAT-COMP-010 | View uploaded documents | Admin reviewing company | 1. Click on document link 2. View/download document | Document opens in viewer/downloads | High
11 | UAT-COMP-011 | Bulk verification | Multiple companies pending | 1. Select multiple companies 2. Click bulk verify | All selected companies verified | Medium
12 | UAT-COMP-012 | Verification audit trail | Company verified | 1. Check audit logs 2. Filter by company | Verification action logged with admin name and timestamp | Medium
13 | UAT-COMP-013 | Company profile completion check | Pelaku usaha logged in | 1. Navigate to profile 2. Check completion status | Profile completion percentage shown | Medium
14 | UAT-COMP-014 | PIC document review | Admin reviewing company | 1. Navigate to PIC section 2. Review PIC documents | PIC documents displayed for review | High
15 | UAT-COMP-015 | Change company status workflow | Company in various statuses | 1. Verify status transitions 2. submitted > in_review > verified 3. submitted > in_review > rejected 4. submitted > in_review > needs_correction > submitted | All valid transitions work correctly | High
16 | UAT-COMP-016 | Prevent invalid status transition | Company in verified status | 1. Try to move to 'submitted' status | Invalid transition blocked | Medium
17 | UAT-COMP-017 | Company verification notification | Company just verified | 1. Login as pelaku usaha 2. Check notifications | Verification status notification received | Medium
18 | UAT-COMP-018 | Verification dashboard metrics | Admin on Company Management | 1. View dashboard metrics 2. Check counts per status | Accurate counts for each status displayed | Low
19 | UAT-COMP-019 | Export company list | Admin on Company Management | 1. Click Export 2. Download file | Company list exported to Excel | Low
20 | UAT-COMP-020 | View verification history | Company with multiple reviews | 1. Open company detail 2. View history tab | All review actions displayed chronologically | Medium
21 | UAT-COMP-021 | Concurrent verification conflict | Two admins reviewing same company | 1. Admin A starts review 2. Admin B starts review 3. Both try to verify | Conflict handled, only one verification succeeds | Medium
22 | UAT-COMP-022 | Company document expiry check | Company documents uploaded | 1. Check document validity dates 2. Flag expired documents | Expired documents highlighted | Low
23 | UAT-COMP-023 | Company search by NIB | Admin on Company Management | 1. Enter NIB in search 2. Submit | Company with matching NIB displayed | Medium
24 | UAT-COMP-024 | Company search by NPWP | Admin on Company Management | 1. Enter NPWP in search 2. Submit | Company with matching NPWP displayed | Medium
25 | UAT-COMP-025 | Company detail print view | Company detail open | 1. Click Print 2. Verify layout | Print-friendly view generated | Low
26 | UAT-COMP-026 | Company list export | Company management page | 1. Click export 2. Download | Company list exported to Excel | Low
27 | UAT-COMP-027 | Verification deadline tracking | Companies pending review | 1. View pending duration 2. Check SLA | Duration since submission displayed | Medium
28 | UAT-COMP-028 | Company document re-upload | Needs correction status | 1. Re-upload corrected document 2. Save | New document replaces old one | High
29 | UAT-COMP-029 | Admin notes persistence | Admin adds notes | 1. Add verification notes 2. Save 3. Reload page | Notes persisted and visible | Medium
30 | UAT-COMP-030 | Company count by status dashboard | Companies in various statuses | 1. View status counts 2. Verify accuracy | Correct count per status displayed | Medium
31 | UAT-COMP-031 | Company sorting | Company list displayed | 1. Sort by name 2. Sort by date 3. Sort by status | Company list sorts correctly by all columns | Medium
32 | UAT-COMP-032 | Company pagination | Many companies registered | 1. Navigate pages 2. Verify data consistency | Company list paginates correctly | Medium
Total Scenarios: |  | 32
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## TDATA
UAT SCENARIOS — Telekom Data Management
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Telekom Data Management
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-TDATA-001 | View telekom data list | User logged in | 1. Navigate to Data Management 2. View data table | Paginated list of telekom data displayed | High
2 | UAT-TDATA-002 | Create new telekom record | User with create permission | 1. Click 'Add New' 2. Fill all fields 3. Save | New record created successfully | High
3 | UAT-TDATA-003 | Edit existing record | Record exists in system | 1. Click Edit on a record 2. Modify fields 3. Save | Record updated successfully | High
4 | UAT-TDATA-004 | Delete record | Record exists in system | 1. Click Delete on a record 2. Confirm deletion | Record deleted, removed from list | High
5 | UAT-TDATA-005 | View record detail | Record exists in system | 1. Click on record 2. View detail page | Full record details displayed | High
6 | UAT-TDATA-006 | Search by company name | Records exist | 1. Enter company name in search 2. Submit | Matching records displayed | High
7 | UAT-TDATA-007 | Filter by service type | Records exist | 1. Select service type filter 2. Apply | Records filtered by service type | High
8 | UAT-TDATA-008 | Filter by status | Records exist | 1. Select status filter 2. Apply | Records filtered by status | Medium
9 | UAT-TDATA-009 | Filter by province | Records exist | 1. Select province filter 2. Apply | Records filtered by province | High
10 | UAT-TDATA-010 | Filter by kabupaten | Province selected | 1. Select kabupaten filter 2. Apply | Records filtered by kabupaten | Medium
11 | UAT-TDATA-011 | Filter by date range | Records exist | 1. Set start date 2. Set end date 3. Apply | Records within date range displayed | Medium
12 | UAT-TDATA-012 | Pagination - next page | More than 1 page of data | 1. Click next page 2. Verify data loads | Next page of data displayed | High
13 | UAT-TDATA-013 | Pagination - page size change | Multiple records | 1. Change page size to 50 2. Verify | 50 records per page displayed | Medium
14 | UAT-TDATA-014 | Sort by column | Records displayed | 1. Click column header 2. Verify sort order | Data sorted by selected column | Medium
15 | UAT-TDATA-015 | Sort ascending/descending toggle | Sorted data | 1. Click same column header 2. Verify sort reversal | Sort order toggled | Medium
16 | UAT-TDATA-016 | Excel import - valid file | User with import permission | 1. Click Import 2. Upload valid Excel 3. Map columns 4. Confirm | Data imported successfully | High
17 | UAT-TDATA-017 | Excel import - column mapping | Import dialog open | 1. Upload Excel 2. Map source to target columns 3. Preview mapping | Columns correctly mapped | High
18 | UAT-TDATA-018 | Excel import - preview data | Columns mapped | 1. Review data preview 2. Verify data accuracy | Preview shows correct data | High
19 | UAT-TDATA-019 | Excel import - invalid data | Import dialog open | 1. Upload Excel with invalid data 2. Attempt import | Validation errors shown, import blocked | Medium
20 | UAT-TDATA-020 | Excel export | Records displayed | 1. Click Export 2. Download file | Excel file downloaded with current data | High
21 | UAT-TDATA-021 | Multi-filter combination | Records exist | 1. Set province filter 2. Set service type filter 3. Set status filter 4. Apply all | Records matching all criteria displayed | Medium
22 | UAT-TDATA-022 | Clear all filters | Filters applied | 1. Click 'Clear Filters' 2. Verify reset | All filters cleared, full data displayed | Medium
23 | UAT-TDATA-023 | Empty state - no results | Filters applied with no matches | 1. Apply filter with no matching data | Empty state message displayed | Low
24 | UAT-TDATA-024 | Record validation - required fields | Create/Edit form open | 1. Leave required fields empty 2. Submit | Validation errors for required fields | High
25 | UAT-TDATA-025 | Location-based data view | Records with location data | 1. Apply location filter 2. View results | Only records from selected location shown | Medium
26 | UAT-TDATA-026 | Batch delete records | Multiple records selected | 1. Select multiple records 2. Click batch delete 3. Confirm | Selected records deleted | Low
27 | UAT-TDATA-027 | Data table column resize | Data table displayed | 1. Drag column border 2. Resize column | Column width adjustable | Low
28 | UAT-TDATA-028 | Data table column visibility | Data table displayed | 1. Toggle column visibility 2. Verify hidden/shown | Columns can be shown/hidden | Low
29 | UAT-TDATA-029 | Data record history/audit | Record modified | 1. View record 2. Check modification history | All changes logged with timestamp and user | Medium
30 | UAT-TDATA-030 | Quick search from table | Data table displayed | 1. Use quick search box 2. Type keyword | Table filters in real-time | Medium
31 | UAT-TDATA-031 | Data validation - numeric fields | Create form open | 1. Enter text in numeric field 2. Verify validation | Numeric validation enforced | Medium
32 | UAT-TDATA-032 | Data validation - date fields | Create form open | 1. Enter invalid date 2. Verify validation | Date validation enforced | Medium
33 | UAT-TDATA-033 | Copy record data | Record displayed | 1. Click Copy 2. Paste in new form | Record data copied for new entry | Low
34 | UAT-TDATA-034 | Record count per service type | Data management page | 1. View service type tabs 2. Check counts | Correct record count per service type | Medium
35 | UAT-TDATA-035 | Data table print view | Data table displayed | 1. Click Print 2. Verify print layout | Print-friendly table layout generated | Low
36 | UAT-TDATA-036 | Data record bookmark | Record detail view | 1. Bookmark record URL 2. Reopen from bookmark | Record detail loads from bookmark URL | Low
Total Scenarios: |  | 36
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## SVC
UAT SCENARIOS — Service Type Pages
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Service Type Pages
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-SVC-001 | View Jasa page | Public user | 1. Navigate to /services/jasa 2. View data | Jasa service data displayed correctly | High
2 | UAT-SVC-002 | View Jaringan page | Public user | 1. Navigate to /services/jaringan 2. View data | Jaringan service data displayed | High
3 | UAT-SVC-003 | View Telsus page | Public user | 1. Navigate to /services/telsus 2. View data | Telsus service data displayed | High
4 | UAT-SVC-004 | View ISR page | Public user | 1. Navigate to /services/isr 2. View data | ISR service data displayed | High
5 | UAT-SVC-005 | View SKLO page | Public user | 1. Navigate to /services/sklo 2. View data | SKLO service data displayed | High
6 | UAT-SVC-006 | View LKO page | Public user | 1. Navigate to /services/lko 2. View data | LKO service data displayed | High
7 | UAT-SVC-007 | View Penomoran page | Public user | 1. Navigate to /services/penomoran 2. View data | Penomoran service data displayed | High
8 | UAT-SVC-008 | View Tarif page | Public user | 1. Navigate to /services/tarif 2. View data | Tarif service data displayed | High
9 | UAT-SVC-009 | Search within service page | Service page open | 1. Use search functionality 2. Enter keyword | Relevant results displayed within service type | Medium
10 | UAT-SVC-010 | Service page responsive | Mobile viewport | 1. Open service page on mobile 2. Verify layout | Page renders correctly on mobile | Low
11 | UAT-SVC-011 | Navigate between services | Service page open | 1. Click navigation to different service 2. Verify data updates | Correct service data loaded | Medium
12 | UAT-SVC-012 | Service data pagination | Service page with many records | 1. Navigate to next page 2. Verify data loads | Pagination works on service pages | Medium
13 | UAT-SVC-013 | Service detail link to full record | Service page open | 1. Click on a record 2. Verify navigation | Navigates to full record detail page | Medium
14 | UAT-SVC-014 | Public data search from homepage | Homepage open | 1. Use search from homepage 2. Enter company or license number | Search results displayed from public data | High
15 | UAT-SVC-015 | Public data view - pagination | Public data view open | 1. Navigate pages 2. Verify data consistency | Pagination works on public data view | Medium
16 | UAT-SVC-016 | Public data view - filter | Public data view open | 1. Apply filters 2. Verify results | Data filtered correctly in public view | Medium
17 | UAT-SVC-017 | Telekom data detail view | Record exists | 1. Navigate to /telekom/:id 2. View full details | Complete record details with related data | High
18 | UAT-SVC-018 | Service type icon/badge display | Service page open | 1. Verify service type badges 2. Check color coding | Correct badges and colors per service type | Low
19 | UAT-SVC-019 | Service page loading skeleton | Service page loading | 1. Navigate to service page 2. Observe loading state | Skeleton/loading indicator shown | Low
20 | UAT-SVC-020 | Service data export per type | Service page open | 1. Click export on service page 2. Download | Service-specific data exported | Medium
21 | UAT-SVC-021 | Cross-service search | Search page open | 1. Search keyword across all services 2. View results | Results from multiple service types shown | Medium
22 | UAT-SVC-022 | Service statistics summary | Service page open | 1. View summary statistics 2. Verify totals | Correct statistics for service type | Medium
23 | UAT-SVC-023 | Service page breadcrumb | Service detail page | 1. View breadcrumb navigation 2. Click parent link | Breadcrumb shows: Home > Services > [Type] | Low
24 | UAT-SVC-024 | Service data card view toggle | Service page open | 1. Toggle between table and card view 2. Verify | Both view modes work correctly | Low
25 | UAT-SVC-025 | Service page URL routing | Direct URL access | 1. Navigate to /services/jasa directly 2. Verify page loads | Service page loads from direct URL | Medium
26 | UAT-SVC-026 | Service type metadata display | Service page open | 1. View service type description 2. Check regulatory info | Service type metadata and description shown | Low
Total Scenarios: |  | 26
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## BPSC
UAT SCENARIOS — BPS Configuration
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: BPS Configuration
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-BPSC-001 | View BPS config page | Admin logged in | 1. Navigate to BPS Configuration | BPS config page displayed with current settings | High
2 | UAT-BPSC-002 | Update API key | BPS config page open | 1. Enter new API key 2. Save | API key updated successfully | High
3 | UAT-BPSC-003 | Set rate limit | BPS config page open | 1. Enter rate limit value 2. Save | Rate limit configured | Medium
4 | UAT-BPSC-004 | Health check - BPS service | BPS config page open | 1. Click Health Check 2. View result | Health status displayed (up/down) | High
5 | UAT-BPSC-005 | Add monitored province | BPS config page open | 1. Click Add Area 2. Select province 3. Save | Province added to monitored areas | High
6 | UAT-BPSC-006 | Add monitored kabupaten | Province selected | 1. Select kabupaten 2. Save | Kabupaten added to monitored areas | High
7 | UAT-BPSC-007 | Remove monitored area | Areas added | 1. Click remove on an area 2. Confirm | Area removed from monitoring | Medium
8 | UAT-BPSC-008 | View monitored areas list | Areas configured | 1. View areas list 2. Verify count | All monitored areas displayed | High
9 | UAT-BPSC-009 | Invalid API key handling | BPS config page open | 1. Enter invalid API key 2. Test connection | Error message displayed, key not saved | Medium
10 | UAT-BPSC-010 | Config persistence after restart | Config saved | 1. Save config 2. Restart application 3. Check config | Config persisted correctly | Medium
11 | UAT-BPSC-011 | BPS base URL configuration | BPS config page open | 1. View/update base URL 2. Save | Base URL configured correctly | Medium
12 | UAT-BPSC-012 | Rate limit enforcement | Rate limit set | 1. Trigger many BPS API calls 2. Exceed rate limit | Rate limiting kicks in, requests queued | Medium
13 | UAT-BPSC-013 | Config validation | BPS config page open | 1. Enter invalid config values 2. Try to save | Validation errors shown | Medium
14 | UAT-BPSC-014 | View API request history | BPS calls made | 1. Navigate to API history 2. View logs | API request log displayed | Low
15 | UAT-BPSC-015 | Multiple area bulk add | BPS config page | 1. Select multiple provinces 2. Add all at once | All selected areas added | Medium
16 | UAT-BPSC-016 | Area coverage indicator | Areas configured | 1. View coverage percentage 2. Check out of 34 provinces | Coverage percentage displayed | Low
17 | UAT-BPSC-017 | Config backup/export | BPS config page | 1. Export current config 2. Download | Config exported for backup | Low
18 | UAT-BPSC-018 | API quota monitoring | BPS config active | 1. View API quota usage 2. Check remaining calls | API quota/usage displayed | Medium
19 | UAT-BPSC-019 | Connection timeout handling | BPS API slow | 1. Simulate slow response 2. Verify timeout handling | Timeout error shown after threshold | Medium
20 | UAT-BPSC-020 | Config change history | Config modified | 1. Modify config 2. Check change log | Config change logged with timestamp | Low
21 | UAT-BPSC-021 | BPS config reset to default | Config modified | 1. Click Reset to Default 2. Confirm 3. Verify values | Config values reset to default settings | Low
Total Scenarios: |  | 21
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## BPSS
UAT SCENARIOS — BPS Survey & Variable Management
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: BPS Survey & Variable Management
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-BPSS-001 | Search BPS catalog | BPS config active | 1. Navigate to BPS Surveys 2. Enter search keyword 3. Search | Matching BPS variables displayed | High
2 | UAT-BPSS-002 | Register new variable | Search results displayed | 1. Select variable from results 2. Click Register 3. Confirm | Variable registered and active | High
3 | UAT-BPSS-003 | View registered variables | Variables registered | 1. Navigate to registered variables list | All registered variables displayed with status | High
4 | UAT-BPSS-004 | Toggle variable active/inactive | Variable registered | 1. Click toggle on variable 2. Verify status change | Variable status toggled | Medium
5 | UAT-BPSS-005 | Delete variable | Variable registered | 1. Click delete on variable 2. Confirm | Variable removed from registered list | Medium
6 | UAT-BPSS-006 | Filter variables by category | Variables registered | 1. Select category filter 2. Apply | Variables filtered by category | Medium
7 | UAT-BPSS-007 | Search within registered variables | Variables registered | 1. Enter keyword in search 2. View results | Matching registered variables shown | Medium
8 | UAT-BPSS-008 | Variable detail view | Variable registered | 1. Click on variable 2. View details | Variable metadata displayed (unit, category, etc.) | Medium
9 | UAT-BPSS-009 | Bulk register variables | Search results with multiple items | 1. Select multiple variables 2. Register all | All selected variables registered | Low
10 | UAT-BPSS-010 | Duplicate variable prevention | Variable already registered | 1. Try to register same variable again | Duplicate warning/prevention shown | Medium
11 | UAT-BPSS-011 | Variable sync status | Variables registered | 1. Check last sync date per variable | Last sync timestamp displayed | Low
12 | UAT-BPSS-012 | Search with no results | BPS catalog search | 1. Search for non-existent keyword | No results message displayed | Low
13 | UAT-BPSS-013 | Category list population | BPS surveys page | 1. Open category filter dropdown | All available categories listed | Low
14 | UAT-BPSS-014 | Variable count per category | Categories displayed | 1. View category list 2. Check count badges | Correct count per category shown | Low
15 | UAT-BPSS-015 | Variable data availability check | Variable registered | 1. Check if data exists for variable 2. View availability indicator | Data availability status shown | Medium
16 | UAT-BPSS-016 | Variable unit display | Variable detail view | 1. View variable metadata 2. Check unit information | Unit of measurement displayed correctly | Low
17 | UAT-BPSS-017 | Variable last sync timestamp | Variable synced | 1. View last sync date per variable | Last sync timestamp shown | Low
18 | UAT-BPSS-018 | Bulk variable status toggle | Multiple variables selected | 1. Select multiple variables 2. Toggle status | All selected variables toggled | Low
19 | UAT-BPSS-019 | Variable export list | Variables registered | 1. Click export 2. Download list | Variable list exported | Low
Total Scenarios: |  | 19
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## BPSV
UAT SCENARIOS — BPS Data Visualization
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: BPS Data Visualization
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-BPSV-001 | View time-series line chart | BPS data synced | 1. Navigate to BPS Visualization 2. Select variable 3. Select area 4. View chart | Line chart showing data over time | High
2 | UAT-BPSV-002 | View bar chart comparison | BPS data synced | 1. Select bar chart view 2. Select multiple areas 3. View chart | Bar chart comparing areas | High
3 | UAT-BPSV-003 | Filter by area | BPS visualization open | 1. Select area from dropdown 2. Apply | Data filtered for selected area | High
4 | UAT-BPSV-004 | Filter by variable | BPS visualization open | 1. Select variable 2. Apply | Data displayed for selected variable | High
5 | UAT-BPSV-005 | Filter by year range | BPS visualization open | 1. Set start year 2. Set end year 3. Apply | Data within year range displayed | High
6 | UAT-BPSV-006 | Multiple area comparison | BPS visualization open | 1. Select 2+ areas 2. View comparison | Multi-line chart with all areas | Medium
7 | UAT-BPSV-007 | View sync history | Sync operations completed | 1. Click sync history tab 2. View log | Sync operations listed with status | Medium
8 | UAT-BPSV-008 | Trigger manual sync | BPS config active | 1. Click 'Sync Now' 2. Wait for completion | Sync executes and history updated | High
9 | UAT-BPSV-009 | Refresh data view | Chart displayed | 1. Click Refresh 2. Verify updated data | Data refreshed from database | Medium
10 | UAT-BPSV-010 | Export chart data | Chart displayed | 1. Click export 2. Download data | Data exported to file | Low
11 | UAT-BPSV-011 | Empty state - no data | No BPS data synced | 1. Open visualization 2. Select area with no data | Empty state message shown | Low
12 | UAT-BPSV-012 | Chart responsive resize | Chart displayed | 1. Resize browser window 2. Verify chart adjusts | Chart resizes responsively | Low
13 | UAT-BPSV-013 | Data tooltip on hover | Chart displayed | 1. Hover over data point | Tooltip shows exact value and date | Medium
14 | UAT-BPSV-014 | Chart type toggle | Chart displayed | 1. Toggle between line and bar 2. Verify data consistency | Same data displayed in different chart types | Medium
15 | UAT-BPSV-015 | Sync status indicator | BPS visualization open | 1. Check sync status badge 2. Verify accuracy | Current sync status shown (idle/syncing/error) | Medium
16 | UAT-BPSV-016 | Full sync execution | BPS configured | 1. Click Full Sync 2. Monitor progress 3. Verify completion | All variables and areas synced | High
17 | UAT-BPSV-017 | Incremental sync | Previous full sync done | 1. Click Incremental Sync 2. Verify only new data fetched | Only new/updated data synced | Medium
18 | UAT-BPSV-018 | Sync error handling | BPS API unavailable | 1. Trigger sync when API is down 2. Verify error handling | Error message shown, graceful degradation | Medium
19 | UAT-BPSV-019 | Data point annotation | Chart with data | 1. Click on data point 2. View annotation options | Annotation/detail for data point shown | Low
20 | UAT-BPSV-020 | Chart print/export | Chart displayed | 1. Click print/export chart 2. Download image | Chart exported as image or PDF | Low
21 | UAT-BPSV-021 | Multiple variable overlay | BPS visualization | 1. Select 2+ variables 2. View overlaid chart | Multiple variables shown on same chart | Medium
22 | UAT-BPSV-022 | Year range boundary validation | Year filter | 1. Set start year > end year 2. Verify validation | Validation error for invalid range | Medium
23 | UAT-BPSV-023 | Auto-refresh data view | Visualization open | 1. Wait for auto-refresh interval 2. Verify data updates | Data auto-refreshes periodically | Low
24 | UAT-BPSV-024 | Data comparison table | BPS data available | 1. Select areas for comparison 2. View table | Side-by-side comparison table shown | Medium
Total Scenarios: |  | 24
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## TPOT
UAT SCENARIOS — Telecom Market Potential
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Telecom Market Potential
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-TPOT-001 | View potential scores table | Scores computed | 1. Navigate to Telecom Potential 2. View scores table | Area scores displayed with tiers (A/B/C/D) | High
2 | UAT-TPOT-002 | View interactive map | Scores computed | 1. Navigate to map view 2. View choropleth | Map displayed with color-coded areas | High
3 | UAT-TPOT-003 | Click area on map | Map displayed | 1. Click on a province/area 2. View popup | Area detail popup with scores shown | High
4 | UAT-TPOT-004 | View radar chart | Area selected | 1. Click area 2. View radar chart | Multi-dimensional radar chart displayed | Medium
5 | UAT-TPOT-005 | View pie chart breakdown | Area selected | 1. Click area 2. View service breakdown | Pie chart showing service distribution | Medium
6 | UAT-TPOT-006 | Sort table by score | Scores table displayed | 1. Click score column header 2. Verify sort | Table sorted by selected score | Medium
7 | UAT-TPOT-007 | Filter by tier | Scores displayed | 1. Select tier filter (A/B/C/D) 2. Apply | Only areas with selected tier shown | Medium
8 | UAT-TPOT-008 | Configure scoring weights | Admin logged in | 1. Open config 2. Adjust weights 3. Save | Weights updated, ready for recompute | Medium
9 | UAT-TPOT-009 | Recompute scores | Config updated | 1. Click 'Compute Scores' 2. Wait for completion | Scores recomputed with new weights | High
10 | UAT-TPOT-010 | V2 scoring with BPS data | BPS data synced | 1. Enable V2 scoring 2. Compute scores | Scores include BPS demand component | Medium
11 | UAT-TPOT-011 | Map zoom and pan | Map displayed | 1. Zoom in/out 2. Pan across map | Map interaction smooth and responsive | Medium
12 | UAT-TPOT-012 | Area detail dashboard | Area clicked on map | 1. Click 'View Details' 2. View area dashboard | Full area dashboard with all metrics | Medium
13 | UAT-TPOT-013 | Service breakdown per area | Area detail open | 1. View service distribution 2. Check counts | Correct service counts per type shown | Medium
14 | UAT-TPOT-014 | Export scores to Excel | Scores displayed | 1. Click Export 2. Download file | Scores exported to Excel file | Low
15 | UAT-TPOT-015 | GeoJSON data endpoint | API available | 1. Request /v2/geojson 2. Verify response | Valid GeoJSON data returned | Medium
16 | UAT-TPOT-016 | Sync pipeline execution | Config set | 1. Click Full Sync Pipeline 2. Monitor progress | Fetch > Compute > Store pipeline executes | High
17 | UAT-TPOT-017 | Year selection | Multiple years available | 1. Select different year 2. View scores | Scores for selected year displayed | Medium
18 | UAT-TPOT-018 | Market activity score detail | Area selected | 1. View market activity breakdown 2. Check components | License count, diversity, and weighted scores shown | Medium
19 | UAT-TPOT-019 | Opportunity score detail | Area selected | 1. View untapped opportunity 2. Check components | Population potential and gap metrics shown | Medium
20 | UAT-TPOT-020 | Config persistence | Config saved | 1. Save config 2. Reload page 3. Verify | Config values persisted correctly | Medium
21 | UAT-TPOT-021 | Tier color coding accuracy | Map displayed | 1. Verify color matches tier 2. Check legend | Colors correctly match A=green, B=blue, C=yellow, D=red | Low
22 | UAT-TPOT-022 | No data handling | New area with no licenses | 1. Compute scores for area with no data | Zero scores handled gracefully, area shown as D tier | Low
23 | UAT-TPOT-023 | Score comparison between years | Multi-year data | 1. Select year A 2. Select year B 3. Compare scores | Year-over-year score comparison shown | Medium
24 | UAT-TPOT-024 | Map legend display | Map rendered | 1. View map legend 2. Check tier labels and colors | Legend correctly shows tier color mapping | Low
25 | UAT-TPOT-025 | Map full-screen mode | Map displayed | 1. Click fullscreen button 2. Verify map fills screen | Map enters fullscreen mode | Low
26 | UAT-TPOT-026 | Score weight validation | Config editor open | 1. Enter weights totaling != 100% 2. Save | Validation error: weights must total 100% | Medium
27 | UAT-TPOT-027 | Area ranking table export | Scores computed | 1. Click export ranking 2. Download | Area ranking exported to Excel | Low
28 | UAT-TPOT-028 | Score percentile calculation | Scores computed | 1. View score percentiles 2. Verify accuracy | Percentile rankings shown correctly | Medium
29 | UAT-TPOT-029 | Score trend analysis | Multi-year scores | 1. Select area 2. View score trend over time | Score trend line chart displayed | Medium
Total Scenarios: |  | 29
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## DASH
UAT SCENARIOS — Dashboard & Analytics
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Dashboard & Analytics
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-DASH-001 | View main dashboard | User logged in | 1. Navigate to Dashboard 2. View KPI cards | Dashboard with service count cards displayed | High
2 | UAT-DASH-002 | KPI cards accuracy | Data exists | 1. View KPI cards 2. Compare with data count | Card counts match actual data counts | High
3 | UAT-DASH-003 | Time-series trend chart | Data exists over time | 1. View trend chart 2. Verify data points | Trend chart shows accurate data over time | High
4 | UAT-DASH-004 | Service distribution chart | Data exists | 1. View distribution chart 2. Verify segments | Correct distribution of services shown | Medium
5 | UAT-DASH-005 | Dashboard auto-refresh | Dashboard open | 1. Wait for auto-refresh interval 2. Verify data update | Dashboard data updates automatically | Medium
6 | UAT-DASH-006 | Dashboard responsive layout | Dashboard open | 1. Resize browser 2. Verify layout adapts | Dashboard components reflow correctly | Low
7 | UAT-DASH-007 | Dashboard loading state | Dashboard navigated to | 1. Navigate to dashboard 2. Observe loading | Loading skeleton/spinner shown while data loads | Low
8 | UAT-DASH-008 | Dashboard error state | API unavailable | 1. Simulate API error 2. View dashboard | Error message displayed gracefully | Medium
9 | UAT-DASH-009 | Quick navigation from dashboard | Dashboard displayed | 1. Click on a KPI card 2. Verify navigation | Navigates to relevant data view | Medium
10 | UAT-DASH-010 | Recent activity feed | Actions performed | 1. View recent activity section 2. Verify entries | Recent actions displayed chronologically | Medium
11 | UAT-DASH-011 | Data freshness indicator | Dashboard displayed | 1. Check last updated timestamp | Last data refresh time displayed | Low
12 | UAT-DASH-012 | Dashboard permission-based content | Different roles login | 1. Login as pelaku_usaha 2. Login as admin 3. Compare dashboards | Content appropriate to role displayed | Medium
13 | UAT-DASH-013 | Enhanced dashboard analytics | Data exists | 1. Navigate to data visualization 2. View analytics | Enhanced charts and analytics displayed | Medium
14 | UAT-DASH-014 | Chart interaction (tooltip/zoom) | Chart displayed | 1. Hover over data points 2. Try zoom/pan | Tooltips shown, chart interactive | Low
15 | UAT-DASH-015 | Dashboard date range filter | Dashboard displayed | 1. Set date range 2. Apply filter 3. Verify KPIs update | KPIs recalculated for selected period | Medium
16 | UAT-DASH-016 | Dashboard export to PDF | Dashboard displayed | 1. Click export 2. Download PDF | Dashboard exported as PDF report | Low
17 | UAT-DASH-017 | Dashboard widget arrangement | Dashboard displayed | 1. View widget layout 2. Verify logical grouping | Widgets arranged logically by importance | Low
18 | UAT-DASH-018 | Dashboard data drill-down | KPI card displayed | 1. Click on KPI card 2. View detailed breakdown | Drill-down shows detailed data behind KPI | Medium
19 | UAT-DASH-019 | Dashboard comparison mode | Dashboard with data | 1. Enable comparison mode 2. Select periods 3. Compare | Side-by-side period comparison shown | Low
20 | UAT-DASH-020 | Dashboard real-time update indicator | Dashboard displayed | 1. Observe real-time indicator 2. Verify pulse/animation | Real-time update indicator visible | Low
Total Scenarios: |  | 20
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## TICK
UAT SCENARIOS — Support & Ticketing
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Support & Ticketing
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-TICK-001 | Create new ticket | User logged in | 1. Navigate to Support 2. Fill ticket form 3. Submit | Ticket created with status 'open' | High
2 | UAT-TICK-002 | View ticket list | Tickets exist | 1. Navigate to tickets 2. View list | Ticket list with status displayed | High
3 | UAT-TICK-003 | Send message on ticket | Ticket open | 1. Open ticket 2. Type message 3. Send | Message sent and displayed in conversation | High
4 | UAT-TICK-004 | Real-time message receive | Ticket open, other party sending | 1. Keep ticket open 2. Other party sends message 3. Verify real-time update | New message appears without refresh (WebSocket) | High
5 | UAT-TICK-005 | Close ticket | Ticket open/in_progress | 1. Click Close Ticket 2. Confirm | Ticket status changed to 'closed' | High
6 | UAT-TICK-006 | Reopen ticket | Ticket closed | 1. Open closed ticket 2. Click Reopen | Ticket status changed back to 'open' | Medium
7 | UAT-TICK-007 | Admin - view all tickets | Admin logged in | 1. Navigate to Admin Tickets 2. View all tickets | All system tickets displayed | High
8 | UAT-TICK-008 | Admin - assign ticket | Unassigned ticket exists | 1. Select ticket 2. Assign to admin 3. Save | Ticket assigned, assignee updated | High
9 | UAT-TICK-009 | Admin - filter by status | Admin tickets page | 1. Filter by status 2. Apply | Tickets filtered by status | Medium
10 | UAT-TICK-010 | Admin - search tickets | Admin tickets page | 1. Enter search keyword 2. Submit | Matching tickets displayed | Medium
11 | UAT-TICK-011 | Unread message counter | New messages received | 1. Check unread badge 2. Verify count | Correct unread count displayed | High
12 | UAT-TICK-012 | Mark messages as read | Unread messages exist | 1. Open ticket 2. Read messages | Messages marked as read, counter decremented | Medium
13 | UAT-TICK-013 | Ticket status transitions | Ticket exists | 1. Verify: open > in_progress > resolved > closed | All valid transitions work | High
14 | UAT-TICK-014 | Ticket SLA tracking | Ticket open for time | 1. Check SLA metrics 2. Verify time tracking | Response time and resolution time tracked | Medium
15 | UAT-TICK-015 | Ticket conversation threading | Multiple messages | 1. View conversation 2. Verify order | Messages displayed in chronological order | High
16 | UAT-TICK-016 | File attachment in ticket | Ticket open | 1. Attach file to message 2. Send | File uploaded and accessible | Medium
17 | UAT-TICK-017 | Ticket notification badge | New ticket created | 1. Check notification area 2. Verify badge | New ticket notification shown | Medium
18 | UAT-TICK-018 | Empty ticket list state | No tickets | 1. View tickets page with no tickets | Empty state message displayed | Low
19 | UAT-TICK-019 | Concurrent messaging | Two users on same ticket | 1. Both users send messages 2. Verify sync | Both messages appear in real-time for both users | Medium
20 | UAT-TICK-020 | Ticket auto-assignment | New ticket, auto-assign enabled | 1. Create ticket 2. Verify auto-assignment | Ticket automatically assigned to available admin | Low
21 | UAT-TICK-021 | WebSocket reconnection | Connection interrupted | 1. Disconnect network briefly 2. Reconnect 3. Verify sync | WebSocket reconnects, messages synced | Medium
22 | UAT-TICK-022 | Ticket priority sorting | Tickets with different priorities | 1. Sort by priority 2. Verify order | High priority tickets shown first | Low
23 | UAT-TICK-023 | Ticket attachment preview | Ticket with attachment | 1. Click attachment 2. Preview in modal | Attachment previewed correctly | Medium
24 | UAT-TICK-024 | Ticket export | Ticket list displayed | 1. Click Export 2. Download | Ticket list exported to Excel | Low
25 | UAT-TICK-025 | Ticket response time tracking | Ticket with response | 1. View ticket metrics 2. Check response time | First response time tracked accurately | Medium
26 | UAT-TICK-026 | Ticket escalation | Ticket open past SLA | 1. Check escalation rules 2. Verify escalation trigger | Ticket escalated after SLA breach | Medium
27 | UAT-TICK-027 | Ticket category/tag | Ticket creation form | 1. Add category/tag to ticket 2. Save 3. Filter by tag | Tickets categorizable and filterable | Low
28 | UAT-TICK-028 | Ticket satisfaction rating | Ticket resolved | 1. Rate ticket resolution 2. Submit rating | Rating recorded for ticket | Low
Total Scenarios: |  | 28
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## FAQ
UAT SCENARIOS — FAQ Management
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: FAQ Management
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-FAQ-001 | View public FAQ | FAQs exist | 1. Navigate to /faq 2. View FAQ list | FAQs displayed with categories | High
2 | UAT-FAQ-002 | Search FAQ | FAQs exist | 1. Enter search keyword 2. Submit | Matching FAQs displayed | High
3 | UAT-FAQ-003 | Filter FAQ by category | FAQs with categories | 1. Select category 2. Apply filter | FAQs filtered by category | Medium
4 | UAT-FAQ-004 | Admin - create FAQ | Admin logged in | 1. Navigate to Admin FAQ 2. Click Add 3. Fill fields 4. Save | New FAQ created | High
5 | UAT-FAQ-005 | Admin - edit FAQ | FAQ exists | 1. Click Edit on FAQ 2. Modify content 3. Save | FAQ updated successfully | High
6 | UAT-FAQ-006 | Admin - delete FAQ | FAQ exists | 1. Click Delete 2. Confirm | FAQ deleted | High
7 | UAT-FAQ-007 | Admin - manage categories | Admin FAQ page | 1. Add/edit/delete categories | Categories managed successfully | Medium
8 | UAT-FAQ-008 | FAQ accordion expand/collapse | FAQ page open | 1. Click on FAQ question 2. Verify answer expands 3. Click again 4. Verify collapse | Accordion expands and collapses | Medium
9 | UAT-FAQ-009 | FAQ ordering | Multiple FAQs | 1. View FAQ order 2. Verify logical ordering | FAQs displayed in correct order | Low
10 | UAT-FAQ-010 | FAQ empty state | No FAQs exist | 1. View FAQ page with no entries | Empty state message shown | Low
11 | UAT-FAQ-011 | FAQ responsive layout | Mobile viewport | 1. View FAQ on mobile | FAQ renders correctly on mobile | Low
12 | UAT-FAQ-012 | FAQ category count | Categories with FAQs | 1. View category list 2. Check count per category | Correct FAQ count per category | Low
13 | UAT-FAQ-013 | FAQ rich text content | Admin FAQ editor | 1. Add formatted text 2. Save 3. View public | Formatted content renders correctly | Medium
14 | UAT-FAQ-014 | FAQ print view | FAQ page open | 1. Click print 2. Verify layout | Print-friendly FAQ layout generated | Low
15 | UAT-FAQ-015 | FAQ share link | FAQ item open | 1. Copy share link 2. Open in new tab | Direct link opens specific FAQ item | Low
16 | UAT-FAQ-016 | FAQ search no results | FAQ page open | 1. Search for non-existent keyword | No results message displayed | Low
17 | UAT-FAQ-017 | FAQ multilingual content | Admin FAQ editor | 1. Enter content in Bahasa 2. Save 3. View public | Bahasa Indonesia content displays correctly | Low
Total Scenarios: |  | 17
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## USER
UAT SCENARIOS — User Management
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: User Management
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-USER-001 | View user list | Admin logged in | 1. Navigate to User Management 2. View user list | All users displayed with roles | High
2 | UAT-USER-002 | Search users | Users exist | 1. Enter username/email in search 2. Submit | Matching users displayed | High
3 | UAT-USER-003 | Edit user details | User exists | 1. Click Edit on user 2. Modify details 3. Save | User details updated | High
4 | UAT-USER-004 | Assign role to user | User exists | 1. Click on user 2. Select role 3. Assign | Role assigned to user | High
5 | UAT-USER-005 | Remove role from user | User has assigned role | 1. Click on user 2. Remove role 3. Confirm | Role removed from user | High
6 | UAT-USER-006 | Filter users by role | Users with different roles | 1. Select role filter 2. Apply | Users filtered by role | Medium
7 | UAT-USER-007 | View user profile details | User exists | 1. Click on user 2. View profile | Full user profile displayed | Medium
8 | UAT-USER-008 | Prevent self-role-removal | Admin viewing own profile | 1. Try to remove own admin role | Action prevented with warning | High
9 | UAT-USER-009 | User activity log view | User has activity | 1. View user 2. Check activity log | User's recent activity displayed | Medium
10 | UAT-USER-010 | User status toggle | User exists | 1. Toggle active/inactive status 2. Verify | User status changed | Medium
11 | UAT-USER-011 | User creation by admin | Admin logged in | 1. Click Add User 2. Fill details 3. Save | New user created with specified role | Medium
12 | UAT-USER-012 | User pagination | Many users exist | 1. Navigate pages 2. Verify data | User list paginates correctly | Low
13 | UAT-USER-013 | User profile view by user | User logged in | 1. Click Profile 2. View own profile | User can view own profile details | High
14 | UAT-USER-014 | User profile update | User logged in | 1. Edit own profile 2. Save changes | Profile updated successfully | High
15 | UAT-USER-015 | User search by email | Admin on user page | 1. Search by email address 2. Verify results | User found by email search | Medium
16 | UAT-USER-016 | User role history | User with role changes | 1. View user 2. Check role change history | Role change history displayed | Low
17 | UAT-USER-017 | User last login display | User list displayed | 1. View last login column 2. Verify dates | Last login timestamp shown per user | Low
18 | UAT-USER-018 | Inactive user identification | Users with no recent login | 1. Filter inactive users 2. Verify criteria | Users inactive > 90 days highlighted | Low
19 | UAT-USER-019 | User export to Excel | User list displayed | 1. Click Export 2. Download | User list exported to Excel | Low
20 | UAT-USER-020 | User password reset by admin | Admin on user detail | 1. Click Reset Password 2. Confirm | Password reset, user notified | Medium
Total Scenarios: |  | 20
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## PERM
UAT SCENARIOS — Permission Management
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Permission Management
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-PERM-001 | View permission matrix | Super admin logged in | 1. Navigate to Permissions 2. View matrix | Permission matrix displayed with roles and modules | High
2 | UAT-PERM-002 | Grant permission to role | Permission matrix open | 1. Select role 2. Select module 3. Grant read/write | Permission granted | High
3 | UAT-PERM-003 | Revoke permission | Permission exists | 1. Select role 2. Uncheck permission 3. Save | Permission revoked | High
4 | UAT-PERM-004 | Bulk permission update | Permission matrix open | 1. Select multiple permissions 2. Save all | All permissions updated in batch | Medium
5 | UAT-PERM-005 | Permission enforcement - allowed | User with read permission | 1. Login as user 2. Access allowed page | Page accessible and functional | High
6 | UAT-PERM-006 | Permission enforcement - denied | User without permission | 1. Login as user 2. Try to access restricted page | Access denied, redirect or error shown | High
7 | UAT-PERM-007 | PermissionGuard component | Protected component | 1. Render component with guard 2. Login as authorized user | Component renders for authorized user | High
8 | UAT-PERM-008 | PermissionGuard - unauthorized | Protected component | 1. Render component 2. Login as unauthorized user | Component hidden or access denied | High
9 | UAT-PERM-009 | Module-level permissions | Permissions configured | 1. Set read-only for module 2. Login as user 3. Try to edit | Read allowed, write blocked | High
10 | UAT-PERM-010 | Field-level permissions | Field permissions set | 1. Set field as hidden for role 2. Login as that role | Field not visible or editable | Medium
11 | UAT-PERM-011 | Permission template apply | Template exists | 1. Select template 2. Apply to role 3. Verify permissions | Template permissions applied to role | Medium
12 | UAT-PERM-012 | Permission change audit | Permission changed | 1. Change permission 2. Check audit log | Permission change logged with details | Medium
13 | UAT-PERM-013 | API permission check | API endpoint | 1. Call API without required permission 2. Verify rejection | 401/403 response returned | High
14 | UAT-PERM-014 | Admin-only pages protection | Non-admin user | 1. Try to access /users, /permissions 2. Verify access denied | Admin pages not accessible to non-admins | High
15 | UAT-PERM-015 | Permission export | Permission matrix | 1. Export permissions 2. Download | Permission matrix exported | Low
16 | UAT-PERM-016 | Permission default reset | Permissions modified | 1. Click Reset to Default 2. Confirm | Permissions reset to template defaults | Low
17 | UAT-PERM-017 | Permission conflict detection | Overlapping rules | 1. Set conflicting permissions 2. Verify handling | Conflict detected and resolved (most restrictive wins) | Medium
18 | UAT-PERM-018 | Permission inheritance chain | Nested permissions | 1. Set parent module permission 2. Check child module 3. Verify inheritance | Child modules inherit parent permissions | Medium
Total Scenarios: |  | 18
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## INTG
UAT SCENARIOS — Integrations Dashboard
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Integrations Dashboard
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-INTG-001 | View all integrations | Integrations configured | 1. Navigate to Integrations 2. View list | All configured integrations displayed | High
2 | UAT-INTG-002 | View integration details | Integration exists | 1. Click on integration 2. View details | Integration config and status shown | High
3 | UAT-INTG-003 | Toggle sync on/off | Integration active | 1. Click toggle for integration 2. Verify status change | Sync enabled/disabled | High
4 | UAT-INTG-004 | View last sync status | Sync completed | 1. View integration card 2. Check status | Last sync status (success/fail) and time shown | High
5 | UAT-INTG-005 | Trigger manual sync | Integration active | 1. Click 'Sync Now' 2. Wait for completion | Manual sync executes, status updates | High
6 | UAT-INTG-006 | View sync error details | Sync failed | 1. Click on failed sync 2. View error | Error message and details displayed | Medium
7 | UAT-INTG-007 | Monitor record count | Sync completed | 1. View integration 2. Check record count | Total synced records count shown | Medium
8 | UAT-INTG-008 | Update integration config | Integration exists | 1. Click Edit 2. Modify config 3. Save | Integration config updated | Medium
9 | UAT-INTG-009 | API integration test dialog | Integration dashboard | 1. Click 'Test Connection' 2. View result | Connection test result displayed | Medium
10 | UAT-INTG-010 | Integration health monitoring | Integrations active | 1. View health status 2. Check all integrations | Health status (green/red) per integration | Medium
11 | UAT-INTG-011 | Sync history per integration | Multiple syncs done | 1. Click on integration 2. View history | Chronological sync history displayed | Medium
12 | UAT-INTG-012 | KOMINFO tariff sync manual | KOMINFO configured | 1. Navigate to KOMINFO sync 2. Click Manual Sync 3. Verify | Tariff data synced from KOMINFO | High
13 | UAT-INTG-013 | KOMINFO sync status | Sync in progress/done | 1. View sync status 2. Verify accuracy | Current sync status displayed | High
14 | UAT-INTG-014 | KOMINFO sync history | Syncs completed | 1. View sync history 2. Check entries | All sync operations listed | Medium
15 | UAT-INTG-015 | KOMINFO synced data view | Data synced | 1. Navigate to synced data 2. View records | KOMINFO tariff data displayed | High
16 | UAT-INTG-016 | e-Telekomunikasi connection test | Config exists | 1. Test connection to e-Telekomunikasi 2. View result | Connection success/failure shown | Medium
17 | UAT-INTG-017 | Integration retry mechanism | Sync failed | 1. View failed sync 2. Click retry 3. Verify retry | Retry mechanism executes and updates status | Medium
18 | UAT-INTG-018 | Integration rate limit indicator | Integration active | 1. View rate limit usage 2. Check remaining quota | Rate limit usage displayed per integration | Low
19 | UAT-INTG-019 | Integration data validation | Data synced | 1. Validate synced data 2. Check completeness | Data integrity verified after sync | Medium
20 | UAT-INTG-020 | Integration schedule configuration | Integration exists | 1. Set sync schedule 2. Save 3. Verify cron | Sync schedule configured correctly | Medium
Total Scenarios: |  | 20
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## SEC
UAT SCENARIOS — Security & DevSecOps
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Security & DevSecOps
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-SEC-001 | CORS enforcement | API available | 1. Make cross-origin request from unlisted origin 2. Verify rejection | Request blocked by CORS policy | High
2 | UAT-SEC-002 | Helmet security headers | API response received | 1. Inspect response headers 2. Check CSP, HSTS, X-Frame | All security headers present | High
3 | UAT-SEC-003 | Rate limiting on auth endpoints | Login endpoint | 1. Send 100+ requests in 15 min 2. Verify rate limit | 429 Too Many Requests returned | High
4 | UAT-SEC-004 | SQL injection prevention | API with input | 1. Send SQL injection payload 2. Verify handling | Input sanitized, no SQL executed | High
5 | UAT-SEC-005 | XSS prevention | Input field | 1. Enter <script> tag in input 2. Submit 3. Verify output | Script tag sanitized, not executed | High
6 | UAT-SEC-006 | JWT token validation | API endpoint | 1. Send request with invalid JWT 2. Verify rejection | 401 Unauthorized returned | High
7 | UAT-SEC-007 | JWT token expiry enforcement | Expired token | 1. Wait for token to expire 2. Make request | 401 returned, token refresh required | High
8 | UAT-SEC-008 | File upload type validation | Upload endpoint | 1. Try to upload .exe file 2. Verify rejection | Invalid file type rejected | High
9 | UAT-SEC-009 | File upload size validation | Upload endpoint | 1. Try to upload >10MB file 2. Verify rejection | File size limit enforced | Medium
10 | UAT-SEC-010 | Audit log recording | Any action performed | 1. Perform data action 2. Check audit_logs 3. Verify entry | Action logged with timestamp, user, details | High
11 | UAT-SEC-011 | Login attempt tracking | Login attempts made | 1. Make several login attempts 2. Check login_attempts table | All attempts recorded | Medium
12 | UAT-SEC-012 | Password hashing verification | User registered | 1. Check password in database 2. Verify hashed | Password stored as bcrypt hash, not plaintext | High
13 | UAT-SEC-013 | Secure cookie flags | Login response | 1. Inspect Set-Cookie header 2. Check flags | httpOnly, secure, sameSite flags set | High
14 | UAT-SEC-014 | HTTPS redirect | HTTP request | 1. Make HTTP request 2. Verify redirect | Redirected to HTTPS | Medium
15 | UAT-SEC-015 | API error handling (no stack traces) | API error triggered | 1. Trigger server error 2. Check response | Generic error message, no stack trace in production | Medium
16 | UAT-SEC-016 | DevSecOps monitoring dashboard | Admin logged in | 1. Navigate to security dashboard 2. View metrics | Security metrics and audit logs displayed | Medium
17 | UAT-SEC-017 | Session management security | User session active | 1. Verify session isolation 2. Check no session hijacking possible | Sessions properly isolated | High
18 | UAT-SEC-018 | Access control on admin routes | Non-admin user | 1. Try to access admin API endpoints 2. Verify rejection | 403 Forbidden returned | High
19 | UAT-SEC-019 | OWASP A01 Broken Access Control | API endpoints | 1. Test IDOR on /telekom-data/:id 2. Access other user's data | Access denied for unauthorized resources | High
20 | UAT-SEC-020 | OWASP A03 Injection | Input fields | 1. Test NoSQL injection 2. Test command injection 3. Verify prevention | All injection attempts prevented | High
21 | UAT-SEC-021 | OWASP A07 Auth Failures | Auth endpoints | 1. Test credential stuffing 2. Test default passwords 3. Verify prevention | Brute force and credential attacks prevented | High
22 | UAT-SEC-022 | Security header X-Content-Type-Options | API response | 1. Check X-Content-Type-Options header 2. Verify nosniff | Header present with nosniff value | Medium
23 | UAT-SEC-023 | Security header X-Frame-Options | API response | 1. Check X-Frame-Options header 2. Verify DENY/SAMEORIGIN | Header present preventing clickjacking | Medium
24 | UAT-SEC-024 | API key rotation | Service key in use | 1. Generate new API key 2. Update config 3. Verify old key rejected | Old key rejected, new key works | Medium
Total Scenarios: |  | 24
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## RBAC
UAT SCENARIOS — RBAC Enforcement
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: RBAC Enforcement
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-RBAC-001 | Super admin - full access | super_admin logged in | 1. Access all pages 2. Access all APIs | All pages and APIs accessible | High
2 | UAT-RBAC-002 | Internal admin - admin access | internal_admin logged in | 1. Access admin pages 2. Verify no user management | Admin pages accessible, user mgmt restricted | High
3 | UAT-RBAC-003 | Pelaku usaha - limited access | pelaku_usaha logged in | 1. Access dashboard 2. Try admin pages 3. Verify restrictions | Dashboard accessible, admin pages blocked | High
4 | UAT-RBAC-004 | Pengolah data - data access | pengolah_data logged in | 1. Access data management 2. Access analytics 3. Try admin pages | Data/analytics accessible, admin blocked | High
5 | UAT-RBAC-005 | Internal group - read access | internal_group logged in | 1. Access data (read) 2. Try to edit 3. Verify restrictions | Read access granted, write blocked | High
6 | UAT-RBAC-006 | Guest - public only | guest role | 1. Access public pages 2. Try protected pages 3. Verify restrictions | Only public pages accessible | High
7 | UAT-RBAC-007 | Role-based sidebar menu | Different roles login | 1. Login as each role 2. Compare sidebar menus | Menu items match role permissions | High
8 | UAT-RBAC-008 | API permission by role | Different roles | 1. Call admin API as pelaku_usaha 2. Verify rejection | Permission denied for unauthorized role | High
9 | UAT-RBAC-009 | Role assignment persistence | Role assigned | 1. Assign role 2. Logout 3. Login again 4. Verify role | Role persists across sessions | High
10 | UAT-RBAC-010 | Multiple role handling | User with multiple roles | 1. Assign multiple roles 2. Verify combined permissions | User gets union of all role permissions | Medium
11 | UAT-RBAC-011 | Role-based data filtering | Data with ownership | 1. Login as pelaku_usaha 2. View data 3. Verify only own data shown | Only user's company data visible | High
12 | UAT-RBAC-012 | Middleware access control | Protected route | 1. Send API request without proper role 2. Check middleware rejection | Access control middleware blocks request | High
13 | UAT-RBAC-013 | Role hierarchy enforcement | Different roles | 1. Verify super_admin > internal_admin > pelaku_usaha 2. Check inheritance | Role hierarchy correctly enforced | High
14 | UAT-RBAC-014 | API data scoping by role | pelaku_usaha logged in | 1. Call /telekom-data API 2. Verify only company data returned | Data scoped to user's company | High
15 | UAT-RBAC-015 | Unauthorized API call logging | Unauthorized request | 1. Make unauthorized API call 2. Check audit log | Unauthorized attempt logged for security review | Medium
16 | UAT-RBAC-016 | Role change immediate effect | User role changed | 1. Admin changes user's role 2. User's next request 3. Verify new permissions | New permissions take effect immediately | High
Total Scenarios: |  | 16
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## NAV
UAT SCENARIOS — Navigation & Layout
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Navigation & Layout
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-NAV-001 | Sidebar navigation | User logged in | 1. Click sidebar items 2. Verify navigation | All sidebar links navigate correctly | High
2 | UAT-NAV-002 | Sidebar collapse/expand | Sidebar visible | 1. Click collapse button 2. Verify sidebar collapses 3. Click expand | Sidebar toggles correctly | Medium
3 | UAT-NAV-003 | Breadcrumb navigation | Deep page open | 1. View breadcrumb 2. Click parent | Breadcrumb shows path, clicking navigates | Medium
4 | UAT-NAV-004 | 404 Not Found page | Invalid URL | 1. Navigate to invalid URL 2. View result | 404 page displayed | Medium
5 | UAT-NAV-005 | Auth redirect - unauthenticated | Not logged in | 1. Try to access protected page 2. Verify redirect | Redirected to login page | High
6 | UAT-NAV-006 | Auth redirect - after login | Redirected to login | 1. Login successfully 2. Verify redirect back | Redirected to originally requested page | Medium
7 | UAT-NAV-007 | Page title updates | Navigate between pages | 1. Navigate to different pages 2. Check browser tab title | Page title updates correctly | Low
8 | UAT-NAV-008 | Loading states | Page loading | 1. Navigate to data-heavy page 2. Observe loading | Loading indicator shown during data fetch | Medium
9 | UAT-NAV-009 | Error boundary | Component error | 1. Trigger component error 2. Verify error boundary | Error boundary catches and displays fallback | Medium
10 | UAT-NAV-010 | Toast notifications | Action performed | 1. Perform action (save, delete) 2. Check toast | Toast notification shown with result | Medium
11 | UAT-NAV-011 | Mobile hamburger menu | Mobile viewport | 1. View on mobile 2. Click hamburger 3. Navigate | Mobile menu opens and navigates | Low
12 | UAT-NAV-012 | Dark mode toggle | Theme toggle available | 1. Toggle dark mode 2. Verify theme change | UI switches between light and dark themes | Low
13 | UAT-NAV-013 | Responsive table layout | Table displayed on mobile | 1. View data table on small screen | Table scrolls horizontally or adapts | Low
14 | UAT-NAV-014 | Keyboard navigation | Any page | 1. Use Tab to navigate 2. Use Enter to activate | All interactive elements keyboard accessible | Low
15 | UAT-NAV-015 | URL deep linking | Specific page URL | 1. Copy URL of a page 2. Open in new browser 3. Verify navigation | Page loads correctly from deep link | Medium
16 | UAT-NAV-016 | Browser refresh state persistence | Page with filters | 1. Apply filters 2. Refresh browser 3. Check state | Filters persist after refresh (or clear gracefully) | Medium
17 | UAT-NAV-017 | Multi-tab navigation | App open in multiple tabs | 1. Open app in 2 tabs 2. Login in tab 1 3. Navigate in tab 2 | Session shared across tabs correctly | Medium
18 | UAT-NAV-018 | Scroll to top on navigation | Long page scrolled down | 1. Scroll down 2. Navigate to new page | New page starts at top | Low
19 | UAT-NAV-019 | Active menu item highlight | Any page open | 1. Navigate to a page 2. Check sidebar | Current page highlighted in sidebar | Low
20 | UAT-NAV-020 | Page transition animation | Navigation between pages | 1. Navigate between pages 2. Observe transition | Smooth page transition without flicker | Low
21 | UAT-NAV-021 | Footer content display | Any page | 1. Scroll to bottom 2. View footer | Footer shows copyright, version, contact info | Low
Total Scenarios: |  | 21
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## EXIM
UAT SCENARIOS — Data Export & Import
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Data Export & Import
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-EXIM-001 | Excel export - full dataset | Data available | 1. Navigate to data page 2. Click Export 3. Download | Excel file with all data downloaded | High
2 | UAT-EXIM-002 | Excel export - filtered data | Filters applied | 1. Apply filters 2. Click Export 3. Download | Only filtered data in export | High
3 | UAT-EXIM-003 | Excel import - valid file | Import dialog open | 1. Upload valid Excel 2. Map columns 3. Import | Data imported successfully | High
4 | UAT-EXIM-004 | Excel import - column mapper | File uploaded | 1. View column mapper 2. Map source to target 3. Verify preview | Columns correctly mapped with preview | High
5 | UAT-EXIM-005 | Excel import - data preview | Columns mapped | 1. Review preview 2. Check data accuracy 3. Confirm | Data preview accurate before import | High
6 | UAT-EXIM-006 | Excel import - validation errors | Invalid data in file | 1. Upload file with invalid data 2. Verify validation | Validation errors shown per row/column | High
7 | UAT-EXIM-007 | Excel import - duplicate detection | Data already exists | 1. Import file with existing records 2. Verify handling | Duplicates detected and handled (skip/update) | Medium
8 | UAT-EXIM-008 | Export with formatting | Data exported | 1. Open exported Excel 2. Check formatting | Excel has proper headers, formatting | Medium
9 | UAT-EXIM-009 | Large file import (1000+ rows) | Large Excel file | 1. Upload large file 2. Import 3. Verify all rows | All rows imported, progress indicator shown | Medium
10 | UAT-EXIM-010 | Import cancel | Import in progress | 1. Start import 2. Cancel mid-process | Import cancelled, no partial data | Medium
11 | UAT-EXIM-011 | PDF document preview | Document uploaded | 1. Click on uploaded document 2. View preview | PDF opens in preview modal | Medium
12 | UAT-EXIM-012 | File download | Documents attached | 1. Click download link 2. Verify file | File downloads correctly | Medium
13 | UAT-EXIM-013 | Excel template download | Import dialog open | 1. Click 'Download Template' 2. Open template | Template Excel with correct columns downloaded | Medium
14 | UAT-EXIM-014 | Import progress indicator | Large file importing | 1. Start large import 2. Observe progress | Progress bar/percentage shown during import | Medium
15 | UAT-EXIM-015 | Export filename convention | Export triggered | 1. Download export 2. Check filename | Filename includes date and module name | Low
16 | UAT-EXIM-016 | Import error log export | Import with errors | 1. Import file with errors 2. Export error log | Error log downloaded with row/error details | Medium
17 | UAT-EXIM-017 | Multi-sheet Excel import | Excel with multiple sheets | 1. Upload multi-sheet file 2. Select sheet 3. Import | User can select target sheet for import | Medium
18 | UAT-EXIM-018 | Data format auto-detection | Excel upload | 1. Upload Excel with dates 2. Check date format detection | Date formats auto-detected and converted | Low
Total Scenarios: |  | 18
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## LOC
UAT SCENARIOS — Location Management
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Location Management
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-LOC-001 | Province selector | Any form with location | 1. Open province dropdown 2. View provinces | All 34 provinces listed | High
2 | UAT-LOC-002 | Kabupaten selector | Province selected | 1. Select province 2. Open kabupaten dropdown | Kabupaten/kota for selected province listed | High
3 | UAT-LOC-003 | Province-kabupaten dependency | Location selector | 1. Select province 2. Change province 3. Verify kabupaten resets | Kabupaten list updates when province changes | High
4 | UAT-LOC-004 | Location data completeness | Location selectors | 1. Check all provinces 2. Spot-check kabupaten lists | All provinces and kabupaten present | Medium
5 | UAT-LOC-005 | Location-based filtering | Data with locations | 1. Filter by province 2. Filter by kabupaten 3. Verify results | Data correctly filtered by location | High
6 | UAT-LOC-006 | Location in data records | Create/edit record | 1. Set location for record 2. Save 3. Verify | Location saved and displayed correctly | High
7 | UAT-LOC-007 | Location search | Location selector | 1. Type in location search 2. Verify suggestions | Matching locations suggested | Medium
8 | UAT-LOC-008 | Location migration tool | Migration needed | 1. Run location migration 2. Verify data updated | Location data migrated correctly | Low
9 | UAT-LOC-009 | Multiple location records | Data management | 1. Create records with different locations 2. Verify each | All locations saved correctly | Medium
10 | UAT-LOC-010 | Location display format | Record with location | 1. View record detail 2. Check location display | Location shows province - kabupaten format | Low
11 | UAT-LOC-011 | Location data integrity check | Location selectors | 1. Check parent-child integrity 2. Verify no orphan kabupaten | All kabupaten have valid parent province | Medium
12 | UAT-LOC-012 | Location code mapping | Location with codes | 1. View location code 2. Verify matches BPS code | Location codes match BPS standard codes | Medium
13 | UAT-LOC-013 | Location autocomplete speed | Location selector | 1. Type location name 2. Measure suggestion speed | Suggestions appear within 300ms | Low
Total Scenarios: |  | 13
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## RT
UAT SCENARIOS — Real-time & WebSocket
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Real-time & WebSocket
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-RT-001 | WebSocket connection establish | User logged in | 1. Login to system 2. Verify WS connection | WebSocket connection established | High
2 | UAT-RT-002 | Real-time ticket message | Ticket open on two clients | 1. Send message from client A 2. Verify appears on client B | Message appears in real-time | High
3 | UAT-RT-003 | Unread count real-time update | New message received | 1. Receive message while on different page 2. Check unread badge | Badge count increments in real-time | High
4 | UAT-RT-004 | WebSocket reconnection | Connection dropped | 1. Simulate network disconnect 2. Reconnect 3. Verify sync | Connection re-established, data synced | High
5 | UAT-RT-005 | Data broadcast on change | Data modified | 1. Modify data from one session 2. Check another session | Data change reflected on other sessions | Medium
6 | UAT-RT-006 | WebSocket authentication | Unauthenticated client | 1. Try WS connection without auth 2. Verify rejection | Unauthenticated WS connection rejected | High
7 | UAT-RT-007 | Multiple concurrent connections | Multiple users online | 1. Connect 10+ users 2. Send messages 3. Verify all receive | All concurrent users receive messages | Medium
8 | UAT-RT-008 | WebSocket message ordering | Rapid messages sent | 1. Send multiple messages quickly 2. Verify order | Messages arrive in correct order | Medium
9 | UAT-RT-009 | Connection status indicator | WebSocket active | 1. View connection status 2. Disconnect 3. Verify indicator | Status shows connected/disconnected | Medium
10 | UAT-RT-010 | Graceful disconnection | User logs out | 1. Logout 2. Verify WS cleanup | WebSocket connection properly closed | Medium
11 | UAT-RT-011 | WebSocket heartbeat/ping | Connection established | 1. Monitor WS connection 2. Check heartbeat interval | Heartbeat keeps connection alive | Medium
12 | UAT-RT-012 | WebSocket message size limit | Large message | 1. Send very large message via WS 2. Verify handling | Large messages handled or rejected gracefully | Low
13 | UAT-RT-013 | WebSocket cross-tab sync | App in multiple tabs | 1. Receive message in tab 1 2. Check tab 2 | Message state synced across browser tabs | Medium
Total Scenarios: |  | 13
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## PERF
UAT SCENARIOS — Performance & Load
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Performance & Load
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-PERF-001 | Page load time < 3s | Any page | 1. Navigate to page 2. Measure load time | Page loads within 3 seconds | High
2 | UAT-PERF-002 | API response < 500ms | API endpoint | 1. Make API request 2. Measure response time | Response within 500ms (p95) | High
3 | UAT-PERF-003 | Pagination performance | Large dataset (1000+) | 1. Navigate pages 2. Measure load time | Each page loads within acceptable time | High
4 | UAT-PERF-004 | Search performance | Large dataset | 1. Execute search 2. Measure response | Search results return within 1 second | Medium
5 | UAT-PERF-005 | Map rendering performance | Telecom potential map | 1. Load map 2. Measure render time | Map renders within 3 seconds | Medium
6 | UAT-PERF-006 | Chart rendering performance | Dashboard with charts | 1. Load charts 2. Measure render time | Charts render within 2 seconds | Medium
7 | UAT-PERF-007 | Excel export performance | Large dataset | 1. Export 1000+ records 2. Measure time | Export completes within 10 seconds | Medium
8 | UAT-PERF-008 | Excel import performance | Large file | 1. Import 1000+ rows 2. Measure time | Import processes within 30 seconds | Medium
9 | UAT-PERF-009 | Concurrent user handling | Multiple users | 1. Simulate 50+ concurrent users 2. Monitor performance | System remains responsive | Medium
10 | UAT-PERF-010 | Database query optimization | Complex queries | 1. Execute complex query 2. Check query time | Query time < 200ms with proper indexing | Medium
11 | UAT-PERF-011 | Memory usage monitoring | Extended session | 1. Use system for extended period 2. Monitor memory | No memory leaks, stable usage | Low
12 | UAT-PERF-012 | Network bandwidth optimization | Page load | 1. Measure transferred data 2. Check compression | Responses gzipped, assets minified | Low
13 | UAT-PERF-013 | Lazy loading verification | Page with many components | 1. Open page 2. Check network tab for lazy chunks | Components lazy loaded on demand | Low
14 | UAT-PERF-014 | Cache invalidation | Data updated | 1. Update data 2. Verify cache updated 3. Check stale data | React Query cache invalidated on mutation | Medium
15 | UAT-PERF-015 | Image optimization | Page with images/icons | 1. Check image sizes 2. Verify format optimization | Images optimized for web delivery | Low
16 | UAT-PERF-016 | Bundle size analysis | Production build | 1. Run build 2. Analyze bundle size | Bundle size within acceptable limits | Low
Total Scenarios: |  | 16
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## ERR
UAT SCENARIOS — Error Handling & Edge Cases
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Error Handling & Edge Cases
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-ERR-001 | Network offline handling | Connection lost | 1. Disconnect network 2. Try to navigate 3. Reconnect | Offline state handled, reconnection seamless | Medium
2 | UAT-ERR-002 | API timeout handling | Slow API response | 1. Simulate slow API 2. Wait for timeout | Timeout error displayed to user | Medium
3 | UAT-ERR-003 | Invalid route handling | Invalid URL | 1. Enter random URL path 2. Verify result | 404 page displayed | High
4 | UAT-ERR-004 | Form validation - all fields | Any form | 1. Submit empty form 2. Verify all validations | All required field errors shown | High
5 | UAT-ERR-005 | Server error handling (500) | API error | 1. Trigger server error 2. Check UI response | User-friendly error message shown | High
6 | UAT-ERR-006 | Session expiry mid-action | Token expires during use | 1. Work in system 2. Token expires 3. Try action | Graceful redirect to login or token refresh | High
7 | UAT-ERR-007 | Concurrent edit conflict | Same record edited by two users | 1. User A edits record 2. User B edits same 3. Both save | Conflict detected, latest save wins or warning shown | Medium
8 | UAT-ERR-008 | Database connection loss | DB goes down | 1. Simulate DB disconnect 2. Make request | Error message shown, no crash | High
9 | UAT-ERR-009 | File upload failure recovery | Upload interrupted | 1. Start file upload 2. Interrupt upload | Upload failure handled, user can retry | Medium
10 | UAT-ERR-010 | Invalid data input handling | Data form | 1. Enter special characters 2. Enter very long strings 3. Submit | Data validated and sanitized | Medium
11 | UAT-ERR-011 | Browser back/forward navigation | Multi-step flow | 1. Use browser back 2. Use browser forward | Navigation works correctly without breaking state | Medium
12 | UAT-ERR-012 | Duplicate submission prevention | Form submission | 1. Click submit rapidly 2. Verify only one submission | Double submission prevented | Medium
13 | UAT-ERR-013 | Unicode/special char handling | Input fields | 1. Enter Unicode characters (emoji, CJK) 2. Save 3. Verify display | Unicode characters stored and displayed correctly | Medium
14 | UAT-ERR-014 | Large text input handling | Textarea fields | 1. Enter very long text (10000+ chars) 2. Save | Long text handled without truncation or error | Medium
15 | UAT-ERR-015 | API 404 handling | Non-existent resource | 1. Request /telekom-data/99999 2. Check response | 404 Not Found with appropriate message | Medium
16 | UAT-ERR-016 | API 422 validation error | Invalid request body | 1. Send malformed request body 2. Check response | 422 with field-level validation errors | Medium
17 | UAT-ERR-017 | Timezone handling | Dates in system | 1. Check date display 2. Verify timezone consistency | All dates display in consistent timezone (WIB) | Medium
18 | UAT-ERR-018 | Pagination boundary - first page | First page of data | 1. Click Previous on first page | Previous button disabled on first page | Low
19 | UAT-ERR-019 | Pagination boundary - last page | Last page of data | 1. Click Next on last page | Next button disabled on last page | Low
20 | UAT-ERR-020 | Empty database handling | Fresh database | 1. Login with no data 2. Navigate all pages | All pages handle empty state gracefully | Medium
21 | UAT-ERR-021 | Special chars in search | Search field | 1. Enter special characters in search 2. Execute search | Search handles special chars without error | Medium
22 | UAT-ERR-022 | Bulk operation progress | Bulk action initiated | 1. Start bulk operation 2. Monitor progress | Progress indicator shows completion status | Low
Total Scenarios: |  | 22
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)

## DEPL
UAT SCENARIOS — Deployment & Health Check
Telkom Insight Hub — Kementerian Komunikasi dan Digital ¦ Module: Deployment & Health Check
No | Scenario ID | Test Scenario | Pre-condition | Test Steps | Expected Result | Priority | Status | Tester | Date | Notes
1 | UAT-DEPL-001 | Health check endpoint | Server running | 1. GET /health 2. Verify response | 200 OK with health status | High
2 | UAT-DEPL-002 | Server startup verification | Fresh start | 1. Start server 2. Verify all services | Server starts, all routes registered | High
3 | UAT-DEPL-003 | Database connection on startup | Server starting | 1. Start server 2. Verify DB connection | Database connected, tables initialized | High
4 | UAT-DEPL-004 | Environment variable loading | Server starting | 1. Set env vars 2. Start server 3. Verify config | All env vars loaded correctly | High
5 | UAT-DEPL-005 | Frontend build verification | npm run build | 1. Run build 2. Verify output | Build succeeds, assets generated in dist/ | High
6 | UAT-DEPL-006 | Frontend serving at /panel/ | Built frontend | 1. Access /panel/ 2. Verify SPA loads | Frontend loads at correct base path | High
7 | UAT-DEPL-007 | API proxy configuration | Dev environment | 1. Start dev server 2. Make API call 3. Verify proxy | Frontend proxy to backend works | Medium
8 | UAT-DEPL-008 | Static file serving | Server running | 1. Request static asset 2. Verify delivery | Static files served correctly | Medium
9 | UAT-DEPL-009 | WebSocket server startup | Server starting | 1. Start server 2. Verify WS endpoint | WebSocket server listening on port 4000 | High
10 | UAT-DEPL-010 | Docker container build | Dockerfile present | 1. Build Docker image 2. Verify success | Docker image builds successfully | Medium
11 | UAT-DEPL-011 | PM2 process management | PM2 configured | 1. Start with PM2 2. Verify process running | Process running, auto-restart configured | Medium
12 | UAT-DEPL-012 | Graceful shutdown | Server running | 1. Send SIGTERM 2. Verify cleanup | Server shuts down gracefully, connections closed | Medium
13 | UAT-DEPL-013 | Database migration on startup | New migrations | 1. Start with pending migrations 2. Verify execution | Migrations run automatically | Medium
14 | UAT-DEPL-014 | Log file creation | Server running | 1. Check log output 2. Verify format | Logs written with proper format and level | Low
15 | UAT-DEPL-015 | CORS config verification | Server running | 1. Send request from allowed origin 2. Send from disallowed | Allowed origins accepted, others rejected | High
16 | UAT-DEPL-016 | Backup and restore verification | Database with data | 1. Create backup 2. Restore backup 3. Verify data | Data fully restored from backup | Medium
17 | UAT-DEPL-017 | SSL certificate verification | HTTPS enabled | 1. Check SSL certificate 2. Verify validity | Valid SSL certificate installed | High
18 | UAT-DEPL-018 | Server restart recovery | Server crashed/restarted | 1. Kill server process 2. PM2 auto-restarts 3. Verify service | Server auto-restarts, no data loss | High
19 | UAT-DEPL-019 | Concurrent deployment | Deployment in progress | 1. Deploy new version 2. Verify zero downtime | Zero downtime deployment achieved | Medium
20 | UAT-DEPL-020 | Environment-specific config | Different environments | 1. Check dev config 2. Check prod config 3. Verify isolation | Environment configs properly isolated | Medium
21 | UAT-DEPL-021 | Disk space monitoring | Server running | 1. Check upload storage space 2. Verify threshold alerts | Low disk space alerts configured | Low
22 | UAT-DEPL-022 | Server timezone configuration | Server running | 1. Check server timezone 2. Verify matches WIB (Asia/Jakarta) | Server timezone set to Asia/Jakarta | Medium
Total Scenarios: |  | 22
Pass
Fail
Blocked
Not Tested
SIGN-OFF / PERSETUJUAN
Peran |  | Nama |  | Jabatan |  | Tanda Tangan |  | Tanggal
Disusun oleh (Prepared by)
QA Lead (Reviewed by)
Project Manager (Approved by)
Stakeholder (Accepted by)